## Hoja1
APIS | Endpoint | Invocan a APIs Terceros | Tactico H2 | ToBe / DynamoDB | UAT/QA
Biometria | POST /v1/biometric/token
Data Consent Management | GET /v7/data_consents_management/parties/{party_id}/consent_agreements
| PATCH /v7/data_consents_management/parties/{party_id}/consent_agreements/{consent_id} | [5 empty] | APIs
Watchlist Screening | POST /v1/watchlist_screening/validate_status |  |  |  |  | Marco | HU1 - KYC
Product Offer | GET /v1/customer_card_position |  | Si (1.0.0) |  | Error 404 | Marco | HU2 - Data Consent Management
KYC | POST /v6/know_your_customer |  |  |  |  | Angel | HU3 - Watchlist Screening
POST /v6/know_your_customer/risk_score
Notificaciones de correo / OTP | POST /v1/emailboxes/{emailbox_id}/emails/{email_id}/classify_email |  |  |  |  | Marco | HU4 - Oferta de productos
POST /v1/emailboxes/{emailbox_id}/send_email
Credit Risk | POST /v1/credit_risk_decisions/decide_risk |  | Si |  | OK | Marco | HU7 - Notificaciones de correo
SKY | POST /v1/customer_benefit_programs/register_customer |  |  |  |  | Marco | HU8 - Registro SKY
[6 empty] | Angel | HU9 - Credit risk
[6 empty] | Marco | HU10 - Gestor documentario
[6 empty] | Angel | HU11 - Reclamos
[6 empty] | Angel | HU - Biometria

## Hoja2
|  | Invocan a APIs Terceros | Tactico H2 | UAT/QA | ToBe / DynamoDB | Listo para Desplegar en Desa
API | Identificación Biométrica (Angel) | Si | Si | Despliegue fallido, por revisar | Feature Listos, en espera de pruebas
REPOSITORIO | cpe-nxhbsc-beidentbiometric
ENDPOINTS
POST | /v1/biometric/token
API | watchlist screening | Si | NA | Desplegado, con error de terceros |  | SI
REPOSITORIO | cpe-nxhbsc-bewatchscreening
ENDPOINTS
POST | /v1/watchlist_screening/validate_status
API | Gestor documental | No | Si | OK, con observaciones por subsanar
REPOSITORIO | cpe-nxhbsc-bedocmanagement
ENDPOINTS
/v2/document_management/documents/{document_id}
DELETE
GET | /v2/document_management/documents/{document_id}/versions
POST | /v2/document_management/download_document
POST | /v2/document_management/search_documents
POST | /v2/document_management/upload_document
API | FIrma digital (es misma api que biometrica) (Angel) | Si | NA | Despliegue fallido, por revisar
REPOSITORIO | cpe-nxhbsc-bedigitsignature
ENDPOINTS
POST | /v1/signature
POST | /v1/signature/attach
POST | /v1/signature/sign
API | Riesgo credito (Angel) | No | Si, debe ir a postgress | Si OK | Feature Listos, en espera de pruebas | SI
REPOSITORIO | cpe-nxhbsc-becreditrisk
ENDPOINTS
POST | /v1/credit_risk_decisions/decide_risk
API | Data consent managment | No | Si | OK, con observaciones por subsanar | Feature Listos, en espera de pruebas | SI
REPOSITORIO | cpe-nxhbsc-bedatacomanagment
ENDPOINTS
GET | /v7/data_consents_management/parties/{party_id}/consent_agreements
POST (Usa Token)
PATCH | /v7/data_consents_management/parties/{party_id}/consent_agreements/{consent_id}
API | Know Your Customer | No | Si | Si, OK | Pendiente
REPOSITORIO | cpe-nxhbsc-beknowyocustomer
ENDPOINTS
POST | /v6/know_your_customer
POST | /v6/know_your_customer/risk_score
API | Ofertas de productos | No | Si | Si, OK (Data en duro) | Pendiente
REPOSITORIO | cpe-nxhbsc-beproducoffering
ENDPOINTS
GET | /v1/customer_card_position/
API | Notificaciones/OTP | Si | Si | Desplegado, con error de terceros | Pendiente
REPOSITORIO | cpe-nxhbsc-beemailboxes
ENDPOINTS
POST | /v1/emailboxes/{emailbox_id}/emails/{email_id}/classify_email
POST | /v1/emailboxes/{emailbox_id}/send_email
API | Registro Sky | Si | NA | Desplegado, con error de terceros |  | SI
REPOSITORIO | cpe-nxhbsc-becustombeprogrm
ENDPOINTS
POST | /v1/customer_benefit_programs/register_customer
API | Api de Reclamos (Angel) | Si | NA | Despliegue fallido, por revisar |  | SI
REPOSITORIO | cpe-nxhbsc-beclaims
ENDPOINTS
POST | /v1/claims/
GET | /v1/claims/{claim_id}
GET | /v1/claims/reasons
GET | v1/claims/reasons/{reason_id}/sub-reasons

## Hoja3
DEV |  | Gestor documental | Data consent managment | Know Your Customer | Notificaciones/OTP | watchlist screening | Riesgo credito | Ofertas de productos | Registro Sky | Api de Reclamos | API Biometria
| Tactico | X |  | X | X |  | X | X |  |  | X
| TOBE | X | X | X | X | X | X | X | X | X | X
UAT
| Tactico | X | X | X | X | X | X | X | X | X | X
TOBE
PROD
Tactico
TOBE
Note on C3: Miguel Quezada Vergaray: Sale hoy 12/06 Dev: Marko ya desplegó
Note on E3: Miguel Quezada Vergaray: Se trabaja sabado y domingo
Note on F3: Miguel Quezada Vergaray: Se trabajará por la noche de hoy 12/06 Dev: Marko salio error en despliegue, revisando
Note on H3: Miguel Quezada Vergaray: Estimamos sacarlo hoy 12/06 Dev: Angel
Note on I3: Miguel Quezada Vergaray: Se trabaja mañana 13/06
Note on J3: Miguel Quezada Vergaray: Se despliega hoy 12/06 dev: marco
Note on K3: Miguel Quezada Vergaray: Se está revisando errores en despliegue Dev: Angel
Note on L3: Miguel Quezada Vergaray: Revisar flujo final Falta credenciales RENIEC Dev: Angel